## Online Gantt 20240315.csv
Name | Start | Finish | Duration | % Complete
Virtual Classroom | 2024-05-02 | 2025-02-25 | 214 days | 0
Design and Prototyping | 2024-05-02 | 2024-06-07 | 27 days | 0
Conducting UX research and creating wireframes | 2024-05-02 | 2024-05-10 | 7 days | 0
Designing UI elements based on wireframes | 2024-05-10 | 2024-05-20 | 7 days | 0
Creating prototypes for each feature | 2024-05-21 | 2024-05-29 | 7 days | 0
Gather feedback and Make adjustments | 2024-05-30 | 2024-06-07 | 7 days | 0
Development | 2024-06-10 | 2024-11-01 | 105 days | 0
Designing Architecture for the System | 2024-06-10 | 2024-07-08 | 21 days | 0
Implementing the backend infrastructure | 2024-07-09 | 2024-08-06 | 21 days | 0
Integration with external services | 2024-08-07 | 2024-09-04 | 21 days | 0
Developing frontend components | 2024-09-05 | 2024-10-03 | 21 days | 0
Integrating both frontend and backend components | 2024-10-04 | 2024-11-01 | 21 days | 0
Testing and Quality Assurance | 2024-11-04 | 2024-12-31 | 42 days | 0
Creating detailed test cases | 2024-11-04 | 2024-11-21 | 14 days | 0
Testing all features using test cases | 2024-11-22 | 2024-12-11 | 14 days | 0
Reporting issues identified | 2024-12-12 | 2024-12-31 | 14 days | 0
Deployment | 2025-01-01 | 2025-02-25 | 40 days | 0
Preparing the environment and configurations | 2025-01-01 | 2025-01-14 | 10 days | 0
Generating Build for final product | 2025-01-15 | 2025-01-28 | 10 days | 0
Creating versions for final release | 2025-01-29 | 2025-02-11 | 10 days | 0
Deploying the final build release build | 2025-02-12 | 2025-02-25 | 10 days | 0
Educator Dashboard | 2024-05-02 | 2025-02-25 | 214 days | 0
Design and Prototyping | 2024-05-02 | 2024-06-07 | 27 days | 0
Conducting UX research and creating wireframes | 2024-05-02 | 2024-05-10 | 7 days | 0
Designing UI elements based on wireframes | 2024-05-10 | 2024-05-20 | 7 days | 0
Creating prototypes for each feature | 2024-05-21 | 2024-05-29 | 7 days | 0
Gather feedback and Make adjustments | 2024-05-30 | 2024-06-07 | 7 days | 0
Development | 2024-06-10 | 2024-11-01 | 105 days | 0
Designing Architecture for the System | 2024-06-10 | 2024-07-08 | 21 days | 0
Implementing the backend infrastructure | 2024-07-09 | 2024-08-06 | 21 days | 0
Integration with external services | 2024-08-07 | 2024-09-04 | 21 days | 0
Developing frontend components | 2024-09-05 | 2024-10-03 | 21 days | 0
Integrating both frontend and backend components | 2024-10-04 | 2024-11-01 | 21 days | 0
Testing and Quality Assurance | 2024-11-04 | 2024-12-31 | 42 days | 0
Creating detailed test cases | 2024-11-04 | 2024-11-21 | 14 days | 0
Testing all features using test cases | 2024-11-22 | 2024-12-11 | 14 days | 0
Reporting issues identified | 2024-12-12 | 2024-12-31 | 14 days | 0
Deployment | 2025-01-01 | 2025-02-25 | 40 days | 0
Preparing the environment and configurations | 2025-01-01 | 2025-01-14 | 10 days | 0
Generating Build for final product | 2025-01-15 | 2025-01-28 | 10 days | 0
Creating versions for final release | 2025-01-29 | 2025-02-11 | 10 days | 0
Deploying the final build release build | 2025-02-12 | 2025-02-25 | 10 days | 0
Student Dashboard | 2024-05-02 | 2025-02-25 | 214 days | 0
Design and Prototyping | 2024-05-02 | 2024-06-07 | 27 days | 0
Conducting UX research and creating wireframes | 2024-05-02 | 2024-05-10 | 7 days | 0
Designing UI elements based on wireframes | 2024-05-10 | 2024-05-20 | 7 days | 0
Creating prototypes for each feature | 2024-05-21 | 2024-05-29 | 7 days | 0
Gather feedback and Make adjustments | 2024-05-30 | 2024-06-07 | 7 days | 0
Development | 2024-06-10 | 2024-11-01 | 105 days | 0
Designing Architecture for the System | 2024-06-10 | 2024-07-08 | 21 days | 0
Implementing the backend infrastructure | 2024-07-09 | 2024-08-06 | 21 days | 0
Integration with external services | 2024-08-07 | 2024-09-04 | 21 days | 0
Developing frontend components | 2024-09-05 | 2024-10-03 | 21 days | 0
Integrating both frontend and backend components | 2024-10-04 | 2024-11-01 | 21 days | 0
Testing and Quality Assurance | 2024-11-04 | 2024-12-31 | 42 days | 0
Creating detailed test cases | 2024-11-04 | 2024-11-21 | 14 days | 0
Testing all features using test cases | 2024-11-22 | 2024-12-11 | 14 days | 0
Reporting issues identified | 2024-12-12 | 2024-12-31 | 14 days | 0
Deployment | 2025-01-01 | 2025-02-25 | 40 days | 0
Preparing the environment and configurations | 2025-01-01 | 2025-01-14 | 10 days | 0
Generating Build for final product | 2025-01-15 | 2025-01-28 | 10 days | 0
Creating versions for final release | 2025-01-29 | 2025-02-11 | 10 days | 0
Deploying the final build release build | 2025-02-12 | 2025-02-25 | 10 days | 0
Game Library Canvas - Iteration 1 | 2024-05-02 | 2025-02-25 | 214 days | 0
Design and Prototyping | 2024-05-02 | 2024-06-07 | 27 days | 0
Conducting UX research and creating wireframes | 2024-05-02 | 2024-05-10 | 7 days | 0
Designing UI elements based on wireframes | 2024-05-10 | 2024-05-20 | 7 days | 0
Creating prototypes for each feature | 2024-05-21 | 2024-05-29 | 7 days | 0
Gather feedback and Make adjustments | 2024-05-30 | 2024-06-07 | 7 days | 0
Development | 2024-06-10 | 2024-11-01 | 105 days | 0
Designing Architecture for the System | 2024-06-10 | 2024-07-08 | 21 days | 0
Implementing the backend infrastructure | 2024-07-09 | 2024-08-06 | 21 days | 0
Integration with external services | 2024-08-07 | 2024-09-04 | 21 days | 0
Developing frontend components | 2024-09-05 | 2024-10-03 | 21 days | 0
Integrating both frontend and backend components | 2024-10-04 | 2024-11-01 | 21 days | 0
Testing and Quality Assurance | 2024-11-04 | 2024-12-31 | 42 days | 0
Creating detailed test cases | 2024-11-04 | 2024-11-21 | 14 days | 0
Testing all features using test cases | 2024-11-22 | 2024-12-11 | 14 days | 0
Reporting issues identified | 2024-12-12 | 2024-12-31 | 14 days | 0
Deployment | 2025-01-01 | 2025-02-25 | 40 days | 0
Preparing the environment and configurations | 2025-01-01 | 2025-01-14 | 10 days | 0
Generating Build for final product | 2025-01-15 | 2025-01-28 | 10 days | 0
Creating versions for final release | 2025-01-29 | 2025-02-11 | 10 days | 0
Deploying the final build release build | 2025-02-12 | 2025-02-25 | 10 days | 0